## How To Apply
KEY Assumptions for use
• These RACI models relate to applying 'how' Applaud and a Partner engage in delivering an Applaud solution to a Client • These RACI models apply varying levels of accountability/responsibility between Applaud and the Partner based on the Partners certification / level of experience • These RACI models are a baseline guide and need to be reviewed, updated and or modified during the Sales and Engagement process with the Partner and or Client to ensure all specifics are captured re- accountability/responsibility of the implementation of the Applaud solution between Applaud and the Partner • For implementation with a Partner under the beginner model, the deal construct could be either Partner led, Applaud led or Jointly led - this would be largely dictated by the client needs
RACI Index:
KEY: R - Responsible (Those who do the work to complete the activity) A - Accountability (Those who own the activity and must assure it is correct and completed) C - Consulted (Those whose opinions are sought; and with whom there is two-way communication) I - Informed (Those who are kept up to date on progress. sometimes after completion of the activity; and with whom there is just one-way communication - this is not always required) RACI Rules: - When applying the RACI model the following rules must be observed - For any single deliverable, there can only be ONE Accountable Party - For any single deliverable, there can be MANY Responsible Parties - For Consulted and Informed, again there can be MANY Parties for a single deliverable
New Partner - Model 1 - Applaud Led
• This RACI model assumes an Applaud primed and led engagement with Partner resource augmentation. For partners with zero or limited levels of training / proficiency, Applaud will lead • At this level, the Partner is likely seeking to 'shadow' KEY tasks and activities led by Applaud in order to gain experience • At this level, the Partner is NOT accountable for ANY deliverables to Applaud or the Client, the resources are merely being utilised on a T&M basis in support of some tasks and activities
Beginner Level Partner - Model 2 - Applaud Led
• This RACI model assumes an Applaud primed and led engagement with the Partner responsible for fixed packages of work • At this level, the Partner has specific Applaud solution experience and can therefore agree with Applaud particular packages of work it will be responsible to deliver at a Fixed Price • At this level, the Partner is accountable for specific deliverables to Applaud on a Fixed Price bases, however Applaud remains accountable to deliver the solution to the Client
Beginner Level Partner - RACI Model 3 - Partner Led
• This RACI model assumes a Partner primed and led engagement with Applaud providing specific roles, assurance or support services • At this level, Applaud provides both a project and solution review and is responsible to the Partner for the delivery of the agreed services • At this level, Applaud is accountable for specific deliverables to the Partner, however the Partner remains accountable to deliver the solution to the Client
Intermediate Level Partner - RACI Model 4 - Partner Led
• This RACI model assumes a Partner primed and led engagement with Applaud providing assurance & essential support services • At this level, Applaud provides a review and recommendation services i.e. assurance, contracting directly with the Partner • At this level, the Partner remains accountable to deliver the end-to-end Applaud solution to the Client
Advanced Level Partner - RACI Model 5 - Partner Led
• This RACI model assumes a Partner primed and led engagement with Applaud providing an optional assurance service • At this level, Applaud will make only recommendations if requested by the partner. For new / innovative design & solutions an assurance layer from Applaud is mandatory • At this level, the Partner remains accountable to deliver the Applaud solution to the Client
Applaud Services & Partner RACI Models - Reference Guide

## New Partner (Model 1)
Phase | Activity |  | Client | SI (Client Side) | Applaud | Partner
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | AR | I
| Customer x Applaud Stand Up | Applaud & Customer
| Customer x Applaud Monthly Executive Review | Applaud & Customer
| Conduct Project Kick-off workshop |  | C | C | AR | I
| Conduct Applaud Workshop Planning |  | C | C | AR | I
| Setup Applaud Development Tenant & Tenant Management |  | I | I | AR | I
| Undertake Integration & Workato Training |  | R | R | AR | R
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer | R | C | AR | I
| Develop Wireframes | Applaud | C | I | AR | I
| Review Wireframes | Applaud & Customer | R | C | AR | I
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer | C | I | AR | I
| Develop Wireframes | Applaud | C | I | AR | I
| Develop Product Backlog | Applaud & Customer | C | I | AR | I
| Story estimation | Applaud & Customer | C | I | AR | I
| Review Wireframes | Applaud & Customer | R | I | AR | I
SETUP SPRINT
| Setup Customer with Github ID's |  |  |  | AR
| Input user stories to Git Hub | Applaud
| Configure SSO | Applaud | c
| Provide access to exisitng API's | Customer | AR
| Install workato agent | Applaud |  |  | AR
| SFTP Access granted to Applaud | Customer | A | R
| Placed model data to to sftp to test integrations | Customer | A | R
| Verifying connections are working | Applaud
| Model structures | Applaud
| Verify integrations are working | Applaud
| Confirm branding is approved | Customer | R |  | A
| Prepare and plan model structure | Applaud
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer
| Execution | Applaud
| i) *Epic title here* | Applaud
| ii) | Applaud
| iii) | Applaud
| iiii) | Applaud
| Internal Demo | Applaud
| Build Config patch | Applaud
| Release to test envirnoment | Applaud
| Customer Demo | Applaud & Customer
| Applaud validate release | Applaud
| Customer Testing | Customer
| Retrospective | Applaud & Customer
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective

## Beginner Partner (Model 2)
Phase | Activity |  | Client | SI (Client Side) | Applaud | Partner
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | AR | I
| Customer x Applaud Stand Up | Applaud & Customer
| Customer x Applaud Monthly Executive Review | Applaud & Customer
| Conduct Project Kick-off workshop |  | C | C | AR | I
| Conduct Applaud Workshop Planning |  | C | C | AR | I
| Setup Applaud Development Tenant & Tenant Management |  | I | I | AR | I
| Undertake Integration & Workato Training |  | R | R | AR | R
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Review Wireframes | Applaud & Customer
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Develop Product Backlog | Applaud & Customer
| Story estimation | Applaud & Customer
| Review Wireframes | Applaud & Customer
SETUP SPRINT
Setup Customer with Github ID's
Input user stories to Git Hub
| Configure SSO | Applaud
| Provide access to exisitng API's | Customer
| Install workato agent | Applaud
| SFTP Access granted to Applaud | Customer
| Placed model data to to sftp to test integrations | Customer
| Verifying connections are working | Applaud
| Model structures | Applaud
| Verify integrations are working | Applaud
| Confirm branding is approved | Customer
| Prepare and plan model structure | Applaud
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer
| Execution | Applaud
| i) *Epic title here* | Applaud
| ii) | Applaud
| iii) | Applaud
| iiii) | Applaud
| Internal Demo | Applaud
| Build Config patch | Applaud
| Release to test envirnoment | Applaud
| Customer Demo | Applaud & Customer
| Applaud validate release | Applaud
| Customer Testing | Customer
| Retrospective | Applaud & Customer
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective

## Beginner Partner (Model 3)
Phase | Activity |  | Client | SI (Client Side) | Applaud | Partner
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | R | AR
| Customer x Applaud Stand Up | Applaud & Customer
| Customer x Applaud Monthly Executive Review | Applaud & Customer
| Conduct Project Kick-off workshop |  | C | C | R | AR
| Conduct Applaud Workshop Planning |  | C | C | R | AR
| Setup Applaud Development Tenant & Tenant Management |  | I | I | C | AR
| Undertake Integration & Workato Training |  | R | R | I | A
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Review Wireframes | Applaud & Customer
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Develop Product Backlog | Applaud & Customer
| Story estimation | Applaud & Customer
| Review Wireframes | Applaud & Customer
SETUP SPRINT
Setup Customer with Github ID's
Input user stories to Git Hub
| Configure SSO | Applaud
| Provide access to exisitng API's | Customer
| Install workato agent | Applaud
| SFTP Access granted to Applaud | Customer
| Placed model data to to sftp to test integrations | Customer
| Verifying connections are working | Applaud
| Model structures | Applaud
| Verify integrations are working | Applaud
| Confirm branding is approved | Customer
| Prepare and plan model structure | Applaud
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer
| Execution | Applaud
| i) *Epic title here* | Applaud
| ii) | Applaud
| iii) | Applaud
| iiii) | Applaud
| Internal Demo | Applaud
| Build Config patch | Applaud
| Release to test envirnoment | Applaud
| Customer Demo | Applaud & Customer
| Applaud validate release | Applaud
| Customer Testing | Customer
| Retrospective | Applaud & Customer
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective

## Intermediate Partner (Model 4)
Phase | Activity |  | Client | SI (Client Side) | Applaud | Partner
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | C | AR
| Customer x Applaud Stand Up | Applaud & Customer
| Customer x Applaud Monthly Executive Review | Applaud & Customer
| Conduct Project Kick-off workshop |  | C | C | C | AR
| Conduct Applaud Workshop Planning |  | C | C | C | AR
| Setup Applaud Development Tenant & Tenant Management |  | I | I | C | AR
| Undertake Integration & Workato Training |  | R | R | I | A
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Review Wireframes | Applaud & Customer
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Develop Product Backlog | Applaud & Customer
| Story estimation | Applaud & Customer
| Review Wireframes | Applaud & Customer
SETUP SPRINT
Setup Customer with Github ID's
Input user stories to Git Hub
| Configure SSO | Applaud
| Provide access to exisitng API's | Customer
| Install workato agent | Applaud
| SFTP Access granted to Applaud | Customer
| Placed model data to to sftp to test integrations | Customer
| Verifying connections are working | Applaud
| Model structures | Applaud
| Verify integrations are working | Applaud
| Confirm branding is approved | Customer
| Prepare and plan model structure | Applaud
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer
| Execution | Applaud
| i) *Epic title here* | Applaud
| ii) | Applaud
| iii) | Applaud
| iiii) | Applaud
| Internal Demo | Applaud
| Build Config patch | Applaud
| Release to test envirnoment | Applaud
| Customer Demo | Applaud & Customer
| Applaud validate release | Applaud
| Customer Testing | Customer
| Retrospective | Applaud & Customer
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective

## Advanced Partner (Model 5)
Phase | Activity |  | Client | SI (Client Side) | Applaud | Partner
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | I | AR
| Customer x Applaud Stand Up | Applaud & Customer
| Customer x Applaud Monthly Executive Review | Applaud & Customer
| Conduct Project Kick-off workshop |  | C | C | I | AR
| Conduct Applaud Workshop Planning |  | C | C | I | AR
| Setup Applaud Development Tenant & Tenant Management |  | I | I | I | AR
| Undertake Integration & Workato Training |  | R | R | I | A
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Review Wireframes | Applaud & Customer
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Develop Product Backlog | Applaud & Customer
| Story estimation | Applaud & Customer
| Review Wireframes | Applaud & Customer
SETUP SPRINT
Setup Customer with Github ID's
Input user stories to Git Hub
| Configure SSO | Applaud
| Provide access to exisitng API's | Customer
| Install workato agent | Applaud
| SFTP Access granted to Applaud | Customer
| Placed model data to to sftp to test integrations | Customer
| Verifying connections are working | Applaud
| Model structures | Applaud
| Verify integrations are working | Applaud
| Confirm branding is approved | Customer
| Prepare and plan model structure | Applaud
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer
| Execution | Applaud
| i) *Epic title here* | Applaud
| ii) | Applaud
| iii) | Applaud
| iiii) | Applaud
| Internal Demo | Applaud
| Build Config patch | Applaud
| Release to test envirnoment | Applaud
| Customer Demo | Applaud & Customer
| Applaud validate release | Applaud
| Customer Testing | Customer
| Retrospective | Applaud & Customer
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective