## PROJECT PLAN
LEGEND
Checkpoint
Activity
| TASK | OWNER | ASSIGNEE | STATUS | START | END | 5 MAY | 6 MAY | 7 MAY | 8 MAY | 10 MAY | 11 MAY | 12 MAY | 13 MAY | 14 MAY | 17 MAY
PRE GO LIVE
| Synch WD Sandbox / Production reports | Client
| Setting up schedule in advance in PROD and start running to correct any chance | Client
| Schedule IMPL refresh from PROD | Client
| Send new RAAS JSON end points for SBX | Client
| Change Freeze on all Integrations, Configuration, Content, Applaud Configuration | Client
| Confirm which reports will have manual data migration and agree on seed | Client
| Final Round of High Priority Testing | Client
| Agreement on the Recovery Plan, Golive support and Ongoing Support, Integration Schedule | Client + Applaud
| Go/No Go Decision | Client + Applaud
| Final synch of WD reports (IMPL to PROD) | Client
| Prepare to run CS integration through Client job system | Client
| Retest RAAS reports in PROD with Applaud PROD credentials before go live | Client + Applaud
GO LIVE ACTIVITES
| Tenant Creation | Infrastructure (Applaud)
| Verify all hotfixes are deployed | Infrastructure (Applaud)
| Enable SSO - Get the entity IDs shared and configured in Azure | Client + Applaud
| Test SSO: Blackberry Access, Affiliates in PROD | Client
| Admin/Setup users(Applaud team) provisioning in PROD and UAT | Infrastructure (Applaud)
| Branding and Asset Migration | Services (Applaud)
| Template Creation from Test/UAT | Services (Applaud)
| Template migration to PROD | Services (Applaud)
| Establish Cornerstone PROD environment | Client
| Work on any outstanding configuration | Services (Applaud)
| Create API Keys for RedCAT, WIKI, Workato (all should be restricted - with PROD instance IPs) | Services (Applaud)
| Verify ACLs across all the models | Services (Applaud)
| Share the keys with the respective teams + Client | Services
| Document Private key for Workato - SFTP connectivity | Integrations (Applaud)
| Test Connectivity with each product and register w SFTP | Client
| Provide Applaud's Workday credentials in PROD | Client
| Provide Applaud's Dovetail credentials in PROD | Client
| Provide Applaud's RedCat credentials in PROD | Client
| Workato PROD tenant creation + access to integration users | Integrations (Applaud)
| Workato recipe migration - Initial Load | Integrations (Applaud)
| Workato recipe scheduling | Integrations (Applaud)
| Applaud to confirm connectivity and working for each integration and Raas | Client + Applaud
| Test Integrations and verify that they used the proper seed file | Client + Applaud
| Manual data migration | Services & Client
Add 'All' value to all the relevant models
Business process types
Task Aggregation types
Mapping - Process Type - Aggregation Type
TimAtTS
FAQs
Resources
Benefit status
Additional benefits
Course Categories
Employee Category
Additional Services
Portal Sections
Quick Links
Tags
Common Requests
| Verify the filters in all blocks of all the pages | Services
| Disable photo upload | Services
| Update settings page - Home page, Sign in page | Services
| Update Dovetail WF with the correct recipe URL | Services + Integrations
| Revoke access to Applaud users (n/a) | Client
| Run initial loads for Config + Employee data | Integrations
| Invite users to PROD | Integrations (Applaud)
| Dovetail Recipe migration | Integration
| Load Public Holidays, Pay schedule (US + Non US) | Integrations
| Public Holidays(Events) | Integrations
| Pay Schedule(Events) | Integrations
| Deactivate all the necessary workflows before initial load | Services
| Initial integration for all pages | Integrations
| My Benefits Integration | Integrations + Services
| My Pay Integration | Integrations + Services
| My Learning Integration | Integrations + Services
| My Wellness Integration | Integrations + Services
| My Time off Integration | Integrations + Services
| My Performance Integration | Integrations + Services
| My Team Integration | Integrations + Services
| AskHR(if any required) Integration | Integrations + Services
| Migrate WF Changes for Inbox Tasks | Services
| Add new property 'Workday tracking id' to Client Task model | Services
| Inbox Tasks Integration | Integrations + Services
| Events data initial load | Integrations + Services
| Verify and activate the workflows | Services + Client
| Enable syncs for all the recipes after workflows are activated | Integrations
| Perform sanity testing | Client
| Revoke Workato access to Applaud users + Hand over | Client
| Initial loads for Performance data | Applaud
| Initial loads for WIKI articles | Applaud
POST GO LIVE
| Checkout of production (confirm data, content, configuration is working as expected) | Client
| Confirmation ready to make available to soft launch users | Client
| Post Production Stabilization (2 weeks) | Client + Applaud
| Training | Applaud
| Internal communication to users to log in to SSO and access Applaud | Client