## Summary
Activities | Start Date | End Date
Pre-cutover
Cutover
Go-live
Open
In Progress
Completed
Closed

## Pre-Cutover Plan
Production Pre-Cutover Activities/Tasks
Milestone | Sl.No. | Dependency | Activity | Responsibility | Status | Duration Hours | Start Date | End Date | Downtime | Documents
1 (pre-cutover - SUP) | 1 |  | Configure On-premise Agent(OPA) in Workato | Applaud
| 2 | 1 | Share the OPA binaries | Applaud
| 3 | 1 | Installation of OPA at on premise | Client
| 4 | 3 | File system setup | Client
| 5 | 3 | Configure PeopleSoft PROD profiles in OPA at on premise | Client
| 6 |  | Firewall rules access between PeopleSoft PROD & OPA | Client
| 7 | 7 | UAT Signoff | Client
2 (pre-cutover - PROD) | 1 |  | Tenant Creation | Applaud
| 2 | 2 | SSO Setup | Applaud
| 3 | 7 | Template creation from UAT | Applaud
| 4 | 7 | Template migration to PROD | Applaud
| 5 | 7 | Checking API Keys migration | Applaud
| 6 |  | Verifying ACL's across all models | Applaud
| 7 | 1 pre cutover SUP & 12 | Validation of http connections and establishing the connections | Applaud
| 8 |  | Workato Recipe migrations( both initial load and sync) | Applaud
| 9 | 5 | Share the list of URL's for all Links for PROD | Client
| 10 | 3 | Share the list of Initial Load file names once copied to server | Client
| 11 |  | Share the list of API's for PROD | Client
| 12 | 3 | Get the opa and http connection credentials | Client
| 13 |  | Document steps on how to create connection so that Client can create the connection themselves | Applaud
| 14 |  | Get approval since we will be getting initial load PROD data for Client | Applaud
| 15 | 3 | Index needs to be added after template creation | Applaud
| 16 | 4 | Check filters in Workflows after template migration | Applaud

## Production Cutover Plan
Production Cutover plan
Milestone | Sl.No. | Dependency | Activity | Responsibility | Status | Duration Hours | Start Date | End Date | Downtime | Document References
| 1 | 4 | Create data for Tags model
| 2 | 4 | Create data for App model
| 3 | 4 | Re attach the filters for every block where tags are used
| 4 | 4 | Re create the update person workflow
| 5 | 1 | Initial loads for all models (Decrypted files)
| 6 | 1 | Sync Recipes to be scheduled as per the decided PROD schedule by client team
| 7 | 1 | Remove the unnecessary HRSS, Identity Manager, Experience designer ACL's and recheck every ACL in every model
| 8 | 1 | Create tenant admin user from client team who will have full access(User details)
| 9 | 1 | Assign HRSS role to the users who will have access to HR Admin pages(user details)
| 10 |  | Branding update for client
| 11 |  | Workato recipe failure mail id's (Support team)
| 12 |  | Removing access for Applaud team from PROD (details and date)