## Implementation Plan
|  |  |  | JUNE | [15 empty] | JULY | [19 empty] | AUGUST | [19 empty] | SEPTEMBER | [24 empty] | OCTOBER
PHASE | TASK | OWNER | STATUS |  | 7 | 8 | 9 | 10 | 11 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
Plan
| Finalise Project Management & Plan | Applaud & Customer | COMPLETED
| Customer x Applaud Stand Up | Applaud & Customer | ONGOING
| Customer x Applaud Monthly Executive Review | Applaud & Customer | ONGOING
Conduct Project Kick-off workshop
Conduct Applaud Workshop Planning
Setup Applaud Development Tenant
Undertake Integration & Workato Training
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Review Wireframes | Applaud & Customer
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer
| Develop Wireframes | Applaud
| Develop Product Backlog | Applaud & Customer
| Story estimation | Applaud & Customer | UPCOMING
| Review Wireframes | Applaud & Customer
SETUP SPRINT
Setup Customer with Github ID's
Input user stories to Git Hub
| Configure SSO | Applaud | UPCOMING
| Provide access to exisitng API's | Customer | ROADBLOCK
| Install workato agent | Applaud | UPCOMING
| SFTP Access granted to Applaud | Customer | ROADBLOCK
| Placed model data to to sftp to test integrations | Customer | ROADBLOCK
| Verifying connections are working | Applaud | UPCOMING
| Model structures | Applaud | UPCOMING
| Verify integrations are working | Applaud | UPCOMING
| Confirm branding is approved | Customer | UPCOMING
| Prepare and plan model structure | Applaud | UPCOMING
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer | UPCOMING
| Execution | Applaud | UPCOMING
| i) *Epic title here* | Applaud | UPCOMING
| ii) | Applaud | UPCOMING
| iii) | Applaud | UPCOMING
| iiii) | Applaud | UPCOMING
| Internal Demo | Applaud | UPCOMING
| Build Config patch | Applaud | UPCOMING
| Release to test envirnoment | Applaud | UPCOMING
| Customer Demo | Applaud & Customer | UPCOMING
| Applaud validate release | Applaud | UPCOMING
| Customer Testing | Customer | UPCOMING
| Retrospective | Applaud & Customer | UPCOMING
BUILD SPRINT 2
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
BUILD SPRINT 3
Sprint Planning Session
Execution
i)
ii)
iii)
iiii)
Internal Demo
Build Config patch
Release to test envirnoment
Customer Demo
Applaud validate release
Customer Testing
Retrospective
UAT
UAT SPRINT 1
Sprint Planning Session
Customer Testing
Team Review
UAT SPRINT 2
Sprint Planning Session
Customer Testing
Team Review
Close
DEPLOYMENT SPRINT
Sprint Planning Session
Final preparation and deployment
Team Review
Go Live
POST GO LIVE SPRINT
Sprint Planning Session
Knowledge Transfer Session
Customer training
Project Retrospective

## Summary Plan
TASK | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26
PLAN
DESIGN SPRINT 1
DESIGN SPRINT 2
SPRINT 0: SETUP
BUILD SPRINT 1
BUILD SPRINT 2
BUILD SPRINT 3
BUILD SPRINT 4
BUILD SPRINT 5
UAT SPRINT 1
UAT SPRINT 2
DEPLOYMENT SPRINT
POST GO LIVE SPRINT

## Resourcing Estimator
|  |  | Resource Estimation | [7 empty] | JUNE | [15 empty] | JULY | [19 empty] | AUGUST | [19 empty] | SEPTEMBER | [24 empty] | OCTOBER
PHASE | TASK | OWNER | Client | SI (Client Side) | Applaud Roles | Effort (Days) | Total | Partner | Effort (Days) | Total |  | 7 | 8 | 9 | 10 | 11 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
Plan
| Finalise Project Management & Plan | Applaud & Customer | R | I | Technical Analyst | 0.2 |  | Business Analyst | 0.5
| Customer x Applaud Stand Up | Applaud & Customer |  |  |  | 0.5 |  | Business Analyst | 0.5
| Customer x Applaud Monthly Executive Review | Applaud & Customer |  |  |  | 0.5 |  | Business Analyst | 0.5
| Conduct Project Kick-off workshop |  | C | C |  | 0.5 |  | Business Analyst | 0.5
| Conduct Applaud Workshop Planning |  | C | C |  | 0.5 |  | Business Analyst | 0.5
| Setup Applaud Development Tenant |  | I | I |  | 0.5 |  | Business Analyst | 0.5
| Undertake Integration & Workato Training |  | R | R |  | 0.5 |  | Business Analyst | 0.5
Design
DESIGN SPRINT 1
| Design Workshops | Applaud & Customer | R | C | Technical Analyst | 0.5 |  | Business Analyst | 0.5
| Develop Wireframes | Applaud | C | I | Project Manager | 0.5 |  | Business Analyst | 0.5
| Review Wireframes | Applaud & Customer | R | C | Project Manager | 0.5 |  | Business Analyst | 0.5
DESIGN SPRINT 2
| Design Workshops | Applaud & Customer | C | I | Technical Analyst | 0.5 |  | Business Analyst | 0.5
| Develop Wireframes | Applaud | C | I | Project Manager | 0.5 |  | Business Analyst | 0.5
| Develop Product Backlog | Applaud & Customer | C | I | Project Manager | 0.5 |  | Business Analyst | 0.5
| Story estimation | Applaud & Customer | C | I | Project Manager | 0.5 |  | Business Analyst | 0.5
| Review Wireframes | Applaud & Customer | R | I | Project Manager | 0.5 |  | Business Analyst | 0.5
SETUP SPRINT
| Setup Customer with Github ID's |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Input user stories to Git Hub |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Configure SSO | Applaud | c |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Provide access to exisitng API's | Customer | AR |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Install workato agent | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| SFTP Access granted to Applaud | Customer | A | R | Project Manager | 0.5 |  | Business Analyst | 0.5
| Placed model data to to sftp to test integrations | Customer | A | R | Project Manager | 0.5 |  | Business Analyst | 0.5
| Verifying connections are working | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Model structures | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Verify integrations are working | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Confirm branding is approved | Customer | R |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Prepare and plan model structure | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
Build
BUILD SPRINT 1
| Sprint Planning Session | Applaud & Customer |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Execution | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| i) *Epic title here* | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| ii) | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iii) | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iiii) | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Internal Demo | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Build Config patch | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Release to test envirnoment | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Demo | Applaud & Customer |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Applaud validate release | Applaud |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Testing | Customer |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Retrospective | Applaud & Customer |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
BUILD SPRINT 2
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Execution |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| i) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| ii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iiii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Internal Demo |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Build Config patch |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Release to test envirnoment |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Demo |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Applaud validate release |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Testing |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
Retrospective
BUILD SPRINT 3
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Execution |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| i) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| ii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| iiii) |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Internal Demo |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Build Config patch |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Release to test envirnoment |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Demo |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Applaud validate release |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Testing |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Retrospective |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
[5 empty] | Project Manager | 0.5 |  | Business Analyst | 0.5
UAT
UAT SPRINT 1
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Testing |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Team Review |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
UAT SPRINT 2
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer Testing |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Team Review |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
Close
DEPLOYMENT SPRINT
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Final preparation and deployment |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Team Review |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Go Live |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
POST GO LIVE SPRINT
| Sprint Planning Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Knowledge Transfer Session |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Customer training |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5
| Project Retrospective |  |  |  | Project Manager | 0.5 |  | Business Analyst | 0.5

## Applaud Roles
Project Manager
Business Analyst
Technical Analyst
End system SME
UX Designer
Integration Specialist
Solution Architect
Business Users (Client Side)
System Integrators (Client Side)

## Effort
0.1
0.2
0.25
0.5
0.75
1

## Applaud Costing Guidance
Sprint Type | Resourcing & Time Commitment Over Course of Sprint | Cost Range per 2-Week Sprint (US$)
Design | Project Manager - 40% Architect / Solution Designer - 60% Principal Consultant - 60% Senior Consultant - 60% | 16500 - 25000
Development | Project Manager - 40% Principal Consultant - 40% Senior Consultant - 100% Associate - 100% | 42000 - 63000
UAT Sprint | Project Manager - 40% Principal Consultant - 40% Senior Consultant - 100% Associate - 100% | 14000 - 21000
Deployment | Project Manager - 40% Principal Consultant - 20% Senior Consultant - 50% Associate - 60% | 9000 - 13500